## Mobile App Feedback
Date | milestone | Device | Workflow | Specific Page/Section | Feedback | Done? | Edward's Comments | Amr's Comments | Rishabh's comments
2020-08-06 | 2 |  | Dashboard | All Tab Menu | Having the hamburger option and the side scrolling header |  | I would get ride of the header and have everything in the hamburger menu. To show which report you are in, under the current header, indicate the current page. Alternatively, we can have only the quick access pages within the scrolling header
2020-08-14 | 2 |  | Login Page |  | When entering the wrong email or password, no prompt is provided to indicate that it is incorrect
2020-08-14 | 2 |  | Dashboard | Tab menu | When under reports or under forms, the side scrolling tab (if we were to keep it) should only contain the things available under that section
2020-08-14 | 2 |  | Home page | quick access icons | From the home page, the quick access icons should be the main 4 most widely used forms & reports in a store.
2020-08-14 | 2 |  | Home page | Profile | When entering DoB, the calendar popup shows the current date but doesn't allow for easy navigation for older years |  | This happens for all DoB sections. Users should be able to easily enter in their date of births
2020-08-14 | 2 |  | Home page | change password | currently, changing password navigates back to the login page. Feels unnatural to navigate to that page right away. Can we have it logout the user after they have submitted a new password and require them to relog?
2020-08-24 | 2 |  | All Date of Birth fields |  | When adding a new patient into the program, we need to ensure that all patients are older than 18 years old. Ensure that they enter a valid date of birth |  | Ensure this is enforced on the dashboards as well
2020-08-24 | 2 |  | All phone number fields |  | Currently, you are able to enter are only 10 digits and that you cannot enter letters or special characters. Ensure that this is enforced | N | Ensure this is enforced on the dashboards as well
2020-08-24 | 2 |  | Pick ups | Picks page | Currently, the submit page is shown as blue when the form is not fully filled in. Please make it grey until the form is fully complete | N
2020-08-24 | 2 |  | Pick ups | Signatures | Is there a way to lock a signature without the need to press save? or is there a way to auto save signatures? | N | Amr wants to find a way to avoid the 2 button clicks needed for save
2020-08-24 | 2 |  | Patient List | Patient reports | Patient lists should be alphabetical and allow users to easily scroll through. We want to follow a similiar scrolling view as contacts Ex: https://drive.google.com/file/d/1kB6z3CWCPRCUwKCwSegKHf9_EzaV3ECH/view?usp=sharing | N
2020-08-24 | 2 |  | Patient List | Patient's address | When adding patients through the app, australian addresses should be the only ones autopopulated | N
2020-08-24 | 2 |  | Add New Patient |  | In the mobile app. Add new patient form should not be visible unless the patient is not on the database, then there should be a+ sign to add new patient once pressed, the form for the new patient should open up. This way not too many forms available, only what is required. | N | Will need a clarification from Amr on how we want to approach this. I am open to suggestions
2020-09-16 | 4 | iOS & Android | Forms workflow | Header bar | The header bar for forms should only show the all forms and not everything. Currently the header bar shows reports and forms. | N
2020-09-16 | 4 | iOS & Android | Forms workflow | Header bar | The order of the forms header bar should go like this (left to right): 1. Pick up calendar 2. Pick ups 3. Checkins 4. Add new Patients 5. Near Misses 6. Returns 7. Patient list 8. Notes for Patient | N
| 4 | iOS & Android | Forms workflow | Search option | Instead of having the search option on the header bar, can we move it as a search icon on the top right? | N
2020-09-16 | 4 | iOS & Android | Login Workflow | Time out | After logging back in after time out, can it go back to the last page the user was in, instead of going back ot the home page? | N
2020-09-16 | 4 | iOS & Android | Pick ups workflow | Pick ups calendar | The home page should have pick up calendars as an easy access icon. | N
2020-09-16 | 4 | iOS & Android | Pick ups workflow | Pick up form | Last pick up date should be a calendar input as well, like DOB | N
2020-09-16 | 4 | iOS & Android | Pick ups workflow | Pick up form | For the "Notes for Patient" textbox, can we allow the user to add indents? | N
2020-09-16 | 4 | iOS & Android | Check in workflow | Check in form | Currently missing the checkin form. Only has the checkin report | N
2020-09-16 | 4 | iOS & Android | Near Misses workflow | Near Misses form | Currently missing the near misses form. Only has the near misses report | N
2020-09-16 | 4 | iOS & Android | Returns workflow | Returns form | For the stores input, will it autopopulate with stores locations relative to the patient's profile? | N
2020-09-16 | 4 | iOS & Android | Profile workflow | Change Password & Change Pin | Can we hide all those options behind profile? | N
2020-09-16 | 4 | iOS & Android | Home page workflow | Home Page | Since every pharmacy will use different pages at different rates, can we allow the admin the ability to determine what pages show up as icons or shortcuts? | N
2020-09-16 | 4 | iOS & Android | Reports workflow | Order of Reports | The order of the reports should go like this (left to right): 1. Pick up reports 2. Check in reports 3. New Patient reports 4. Near Misses reports 5. Returns reports 6. Patient Notes reports | N
2020-09-16 | 4 | iOS & Android | Reports workflow | Filtering of Reports | Since on the mobile app, reports show up as cards, it would be good to be able to set the dates for review. Full length reports will be usually viewed on the dashboard Ex: I may only want to view the reports from this week, so I would set a date filter for this week on the mobile app | N
2020-09-18 | 4 | iOS | Hamburger menu workflow | Bringing out menu from the side | When I open up the Hamburger menu by swiping from the side, it always navigates my active page back to home or a previous page. I would want it to stay on the same page prior to bringing up the hamburger menu | N
2020-09-18 | 4 | iOS & Android | Time out workflow | Time out duration | Currently it times out after a set duration. Would we be able to change that for the app from the admin panel or on the devices themselves with the approriate user logged in? | N
2020-09-24 | 4 | iOS & Android | Pick ups workflow | Number format within Pick up form | When clicking on "Weeks Last Picked" & "Number of Weeks to be picked up", instead of showing the full keyboard, please show a numeric keyboard. This is to ensure that only valid numbers are input | N
2020-09-24 | 4 | iOS & Android | Pick up workflow | "Who Is Picking Up" | When the carer option is selected, a new input field should pop up asking for the carer's name. After that is entered, that is saved to that Patient's profile and will be the default option for future pick ups | N
2020-09-24 | 4 | iOS & Android | Pick up workflow | Date of Birth input field | Have the calendar popup be like the apple version? | N | I will look to get a screen shot from Amr
2020-09-24 | 4 | iOS & Android | Pick up workflow | Retraction of Keyboard | The keyboard does not disappear after the user has entered their content. There is also no option to retract or hide the keyboard | N
2020-09-24 | 4 | iOS & Android | New Patient workflow | Text message option | The "get a text when picked up/Delivered" option should be default by nature when adding a new patient | N
2020-09-24 | 4 | iOS & Android | New Patient workflow | Phone number validation | How would we validate that the phone number provided is a valid phone number? | N | It may be difficult to validate a phone number at the time of pick up. What does phone number validation work in your mind @Amr? | 10 digits starting with 04 xxxx xxxx
2020-09-24 | 4 | iOS & Android | Pick up workflow | Input fields | How can we easily navigate to the next input field? | N
2020-09-24 | 4 | iOS & Android | Pick up workflow | Date format | The dates would be in this format "dd/mm/yyyy" | N | Have this format be the default for all date related fields
2020-09-24 | 4 | iOS & Android | Pick up workflow | Notes section | Currently all notes are in a single line format. Allow for multi line text. | N | No need for bullet points I believe
2020-09-24 | 4 | iOS & Android | Pick up workflow | Mandatory fields | When a mandatory field is not entered, and the user is trying to save, one of the two following actions should happen 1. The save button is greyed out 2. The forms scrolls back to the input field that is missing a mandatory input | N
2020-10-08 | 4 | iOS & Android | Pick up workflow | Mandatory fields | Currently unable to enter information into Date of Birth & Weeks last picked up fields
2020-10-08 | 4 | iOS & Android | New Patient workflow | Facility field drop down | When trying to select facility, the drop down menu appears above the menu option. Please ensure that it is a proper drop down menu
2020-10-08 | 4 | iOS & Android | Pick Up Calendar workflow | Calendar home screen | Screen goes blank after I try to add something in the calendar via the "+" button
2020-10-20 |  |  | Calendar home page | Calendar home screen | Technician login: 1. Pick up form 2. Patient search 3. Add new patient 4. Settings Pharmacist login: 1. Check in form 2. Pick up form 3. Add new patient 4. Settings
|  |  |  | Pick up forms | Removing of header bar & replace w/ new design Edward has suggested
|  |  |  | Profile | 1. Remove phone number and replace with email address 2. Edit User Profile instead of Edit Profile 3. Signature reference as well
|  |  |  | Pick up forms | Patient name: Instead of "Enter Patient name" have "Last, First". Use Zoho as a reference. When entering names, user will be actively filtered
|  |  |  | Pick up forms | When looking for searching for a patient's names on the pick up form, there is an "add patient" button next to the search bar. Refer to Zoho video
|  |  |  | Pick up forms | Location chck box is not aligned
|  |  |  | Pick up forms | Hard to navigate past signature. Options: 1. Either have a scrolling bar to move around on the page 2. Have a tap to add signature, similiar to Zoho mobile app
|  |  |  | Pick up forms | Notes for Patient should not be a mandatory field.
|  |  |  | Pick up forms | When a mandatory field is missing, navigate to the missing mandatory fields. Outline in red what is missing in mandatory
|  |  |  | Pick up forms | A patient's profile will auto load into the pick up form when a patient is selected. Ex: If the patient has medication that is stored in the safe, the "Safe" location will be ticked automatically upon future pick ups.
|  |  |  | Pick up forms | When carer is selected, a new line will be provided with a text box to enter the Carer's name. This will be saved to the patient's profile
|  |  |  | Check in form | When "Notes for Patient" is added during checking, it will show up for the Patient's next pick up form. The date of when the note was added is also time stamped. The history of the "Notes for Patient" will be available in the reports
|  |  |  | Check in form | If DD is checked off during check in, then location will automatically be in safe
|  |  |  | Pick up reports | For reports, show on a per patient basis. Be able to select a patient and then show all the specific reports for that patient Also only show 3 months worth of pickups per patient. Admin will be able to see all the pick ups |  | This format should be the same for all reports
|  |  |  | Add new patient form | Only be available during pick up flow or from main dashboard. No specific page within forms
|  |  |  | Add new patient form | Facilities are usually private patients or nursing homes or community patients. FAcilities are not linked directly to a pharmacy or its subscription. Just used as an internal data point for admin Be able to add new facilities during "Add New Patient" form
|  |  |  | Add new patient form | When "Get a text when picked up/Delivered?" is selected, users will be notified via SMS of pick up. The toggle flow must follow the same as Zoho.
|  |  |  | Add new patient form | Mobile number entry will need to meet validation requirements |  | Amr to provide mobile number standards for AUS
|  |  |  | Add new patient form | When adding patient, it doesn't double check to see if patient already exists. Need to do DB validation during Patient adding process.
|  |  |  | Add new patient form | During adding process, also add a final check saying "Are you sure you want to add this person?"
|  |  |  | Add new patient form | DOB: selecting dates is in the american format.
|  |  |  | Add new patient form | DOB: easier to select later dates
|  |  |  | Add new patient form | When DOB < 18, open another page that requires the patient to check a consent box acknowledging that they are have the consent from a parent/guardian. |  | Text content will be provided by Amr
|  |  |  | Pick up calendar | Follow the same format as Zoho mobile. The calendar would be able to show what was picked up on each day via cards. Pick up calander is used mainly for planning a Pharmacist or Technician's day We would also want a indicator showing who is "Going To" pick up on that specific date. It will show the "scheduled" pick up. If a patient picks up before the "scheduled" date, a new "scheduled" date will be booked, depending on their weeks picked up
|  |  |  | Pick up calendar | In Zoho, there is a total count on the bottom right. This is to show how many pick up orders occured this month |  | Amr will need to figure out whether to show the total number of pick ups a month or the total unique patient pick up
|  |  |  | Patient list | Not needed anymore |  | Confirm with Amr
|  |  |  | New Patient report | Not needed anymore
|  |  |  | All returns | All returns should be called "Returns report"
|  |  |  | Search | Move to the top right as a search bar/magnifying glass

## Admin & Pharmacy Dashboard
Date | milestone | Location | Workflow | Specific Page/Section | Feedback | UI or Data | Done? | Edward's Comments | Amr's Comments | Rishabh's comments
2020-08-14 | 2 | Admin | Pick ups | Pick up calendar | Is there going to be a calendar view for the pickups? |  | Y
2020-08-14 | 2 | Admin | Pharmacy | Pharmacy registration | When confirming a password, the password itself shows up still, instead of being hidden |  | Y
2020-08-15 | 2 | Admin | Pharmacy | Pharmacy registration | Phone numbers should have a defined format. Must follow region based forwards and provide an example. Ex: For Canada, +1 should follow the format 123-456-7890 |  | N/A |  |  | Please provide australian format
2020-08-16 | 2 | Admin | Pharmacy | Pharmacy registration | If a field is not filled when registering, can we not have all the fields erased? Keep anything that has already been filled in |  | Y |  |  | Can you explain this more?
2020-08-16 | 2 | Admin | Pick ups | Non-pick up related pages | Can we move the following pages & reports into a seperate section? It would be easier to find these reports and pages if they were seperated into a Patient section & a compliance section 1. 6 month compliance report 2. All compliance index report 3. Add new patient 4. New patient report 5. Patient picked up last month |  | Y
2020-08-24 | 2 | Admin | All forms |  | Create either a quick access section that shows only the frequently used reports & forms or have a quick short-cut tab within the main dsahboard |  | N/A
2020-09-24 | 5 | Admin | Pick ups Calender workflow | Pick up calendar | Can we have the calendar utilize more space within the home page? There is currently too much white space on the dashboard |  | Y
2020-10-20 | 6 | Super Admin & Pharmacy Admin |  | Settings | Be able to add alter time out of app |  | N/A
2020-10-21 | 6 | Super Admin |  | Dashboard home page | Quick link to the following: 1. Pharmacies 2. Technicians 3. Patients 4. Pick Ups 5. Settings
2020-10-21 | 6 | Super Admin |  | Hamburger menu | Breakdown: 1. Stores/Pharmacy 2. Subscription settings 3. Reports 4. Automation N/A 5. Logs
2020-10-21 | 6 | Super Admin |  | Stores | Options: 1. Manage stores 2. Add new stores
2020-10-21 | 6 | Super Admin |  | Subscription settings | Keeps the same
2020-10-21 | 6 | Super Admin |  | Reports | All reports will be under here. Move the following under the Reports sections: 1. Pick ups 2. Checking 3. Near Misses 4. Returns 5. Audits
2020-10-21 | 6 | Super Admin |  | Add Patients | Have it as a seperate section, like it currently right now. Be able to add patients, view patient info, manage patient Also move notes for patient to patients |  | Y
2020-10-21 | 6 | Super Admin |  | Search | Search section right now is redundant.
2020-10-21 | 6 | Super Admin |  | Logs | Ability to view the access logs of stores, pharmacists & technicians. The use case for this would be to view and manage access logs of anyone using all instances of the applicaiton. |  |  | Have this shown on the manage "people" page?
2020-10-21 | 6 | Super Admin |  | Automation Section | In this section, we want to be able to select which reports we can have automatically generated and when it will generate. This section will have the following: 1. Toggle to turn on and off auto report generation 2. Report name 3. Monthly generation only. Also want the 6 month option. 4. Be able to choose default email to send too These reports will be sent via one email with the reports attached as PDF or excel docs. The pharmacy will be able to select and choose the report format. |  | N/A
2020-10-21 | 6 | Super Admin |  | Pharmacy Registration | Order of text fields (from left to right): 1. Phone number 2. First name 3. Last name 4. Email |  | y | Follow the same order as the email that Amr sent
2020-10-21 | 6 | Super Admin |  | Pharmacy management | Be able to have a page where the super admin can edit their pharmacy page, incouding things like company name, password, email, website link, etc
2020-10-21 | 6 | Super Admin |  | Pharmacy Registration | No need to have +04. Only need to enter in 10 digit phone number w/ area code
2020-10-21 | 6 | Super Admin |  | Pharmacies page access | Be able to bulk turn on and off fields |  | N/A | Talk to Rishabh to find a way to do bulk actions
2020-10-21 | 6 | Pharmacy Admin |  | Dashboard home page | Options: 1. Pharmacists 2. Patients 3. Technicials 4. Pick up calendar 5. Notification settings
2020-10-21 | 6 | Pharmacy Admin |  | Add Patients | Have fields move left to right, top to bottom |  |  | Have this be the standard for text fields
2020-10-21 | 6 | Pharmacy Admin |  | Add Patients: Address | When entering address, it only shows location and not street address. |  |  | This feature works in the "Add Technician" field
2020-10-21 | 6 | Pharmacy Admin |  | Add Patients: Mobile number | Change it to "Mobile number" Have the field format be XXXX XXXX also have a visual check showing whether you have entered the correct phone or are missing a digit |  |  | All mobile phone numbers are starting at 04 at the base, so remove that from the text field
2020-10-21 | 6 | Pharmacy Admin |  | Add Patients: locaiton | Currently needs to have all fields selected. The user should only need to select one or more, not all
2020-10-21 | 6 | Pharmacy Admin |  | Add Patients: get text | Instead of same as above, have a check box saying "secondary number" and when the admin selects that, a drop down will show
2020-10-21 | 6 | Pharmacy Admin |  | Add Patients | Ability to import patients via .csv file. The .csv file must have all the mandatory fields Move add patient button to the middle |  |  | Will need to talk to Rishabh about what happens there is a missing field. Will we be able to notify a the admin of fields that are missing
2020-10-21 | 6 | Pharmacy Admin |  | Add Technicians | Clarify the "This email will be use for pharmacy login also" message
2020-10-21 | 6 | Pharmacy Admin |  | All Technicians | Unable to edit technician information from this page
2020-10-21 | 6 | Pharmacy Admin |  | All Technicians | Be able to change their account access status. Ex: Active vs inactive |  | N/A
2020-10-21 | 6 | Pharmacy Admin |  | Terminating Active mobile app sessions | Be able to terminate mobile app sessions |  | N/A | Possible future enhancements. Talk to Rishabh on whether this is possible
2020-10-21 | 6 | Pharmacy Admin |  | Pick ups | No need to have 6 month & monthly reports. These will be replaced with the automated report generation. Also field filtering will remove the need for different "monthly" reports |  |  | Same for all reports
2020-10-21 | 6 | Pharmacy Admin |  | Pick up calendar | Have in the main dashboard. Also have the calendar fit all into one view without scrolling |  | y
2020-10-21 | 6 | Pharmacy Admin |  | Pick up calendar | Pick up total will show on the bottom right and will calculate the number of unique pick ups per patient |  | N/A
2020-10-21 | 6 | Pharmacy Admin |  | Add Pickups | Unable to type the name of patients. When typing, be able to show the matching patient names |  |  |  |  | can we add pickup for patients which is not added
2020-10-21 | 6 | Pharmacy Admin |  | Add Pickups: Last Pick up date | No text field currently. these will be auto filled from latest records. Also be a different font colour
2020-10-21 | 6 | Pharmacy Admin |  | Add Pickups: # of weeks last picked up | No text field currently. these will be auto filled from latest records. Also be a different font colour
2020-10-21 | 6 | Pharmacy Admin |  | Add Pickups: Location | Admin only needs to select one or more. Also this is linked to the checking files, like the mobile application
2020-10-21 | 6 | Pharmacy Admin |  | Add Pickups: Signature | What does "show points" mean? If carer is shown, the header for "Patient Signature" should change to "Carer Signature" |  | y
2020-10-21 | 6 | Pharmacy Admin |  | Add Pickups: Who is picking up? | When an option is selected, no colour shows. Option that is selected during the first pick up will be the default for future pick ups for that patient |  | need to discuss
2020-10-21 | 6 | Pharmacy Admin |  | Add Pickups: Notes from Patient | Not a mandatory field
2020-10-21 | 6 | Pharmacy Admin |  | Add Pickups | Change button to "submit" and move it to the middle and botton |  | y
2020-10-21 | 6 | Pharmacy Admin |  | Add Pickups | If there is a missing field and the user hits submit, move the cusor to the first missing field. Also keep all fields except for wrong or missing fields, when user hits submit |  | N/A | Have this be the default action for all forms
2020-10-21 | 6 | Pharmacy Admin |  | Add Pickups: date of birth | Minimum prescription pick up age is 12 years old. From 12 - 18, they will have to sign a consent form |  | need to discuss | Have as default for all forms
2020-10-21 | 6 | Pharmacy Admin |  | Pick up reports | Have a date filter on the date column. Split Date - Time to 2 seperate columns
2020-10-21 | 6 | Pharmacy Admin |  | Pick up reports | Have a data field that shows pick ups that were scheduled but not picked up. Admin wants to be able to easily see who did not pick up for specific months |  | need to discuss
2020-10-21 | 6 | Pharmacy Admin |  | Checking: DD | When DD is selected, the location will be immediately set as safe. |  | y | Format and location looks funny from Amr's perspective
2020-10-21 | 6 | Pharmacy Admin |  | Checking: Patient | Want to be able to check in multiple patients with the same number of weeks of prescription |  |  | This is the only form that allows for multiple patient checkins because Amr may get multiple webster packs at the same time with the same number of week durations
2020-10-21 | 6 | Pharmacy Admin |  | Add Returns | Order of text fields (from left to right): 1. Name 2. DOB 3. Store 4. Select Days or weeks 5. # of days/weeks 6. Staff initials |  |  | Looking for opinion on how to select different days or weeks
2020-10-21 | 6 | Pharmacy Admin |  | Add Returns | Staff initials will be a mandatory field |  |  | This should be the date standard for the entire application
2020-10-21 | 6 | Pharmacy Admin |  | DOB | Standard should be DD/MM/YYYY
2020-10-21 | 6 | Pharmacy Admin |  | Near Misses: Error Type | Add "Error Type" Header to the near misses options |  | Explanation need
2020-10-21 | 6 | Pharmacy Admin |  | Near Misses: Initials | Initials field should be smaller. Only need to be big enough for initials
2020-10-21 | 6 | Pharmacy Admin |  | Near Misses: Error Type check boxes | Add "Other" as a check box and a text field would pop up when selected Not mandatory as well
2020-10-21 | 6 | Pharmacy Admin |  | Near Misses report | Also have a date timestamp and then have a date filter available as well
2020-10-21 | 6 | Pharmacy Admin
2020-10-21 | 6 | Pharmacy Admin |  | Report style | May want to change layout and color. Data is good |  |  | May want to follow the same format as Zoho as it looks more appealing.
2020-10-21 | 6 | Pharmacy Admin |  | Search | Be able to search by Mobile number |  | N/A
2020-10-21 | 6 | Pharmacy Admin |  | Search | When opening search, all the headers open up |  | N/A